## Assessment Sheet (hidden)
Process Guideline:PMs to make a copy of this template to start any updates for their delivery The Checklist should be placed in the g-drive respective project folder < https://drive.google.com/drive/folders/0B3PjiaId2BOmb3N5azNQN09CYXM > PM's to complete the RISK ASSESSMENT SECTION by selection appropriate option in column B. The Release Risk Assessment is derived form Q26 to R29. The Risk Score will be derived using table in Q8 to R20. The Checklists needs to be updated by PM's and then reviewed and assesed by the SQM, which will derive the GATES SCORE Based on the RISK ASSESSMENT and GATES SCORE, the Release readiness RED/AMBER/GREEN is derived from Q2 to U6. These scores will be discussed at the Release Go/NoGO call which will provide the final decision. | [12 empty] | Reference and guideline to Assessment
[14 empty] | Risk Assessment |  |  | Go/NoGo Call inference
[14 empty] | Low | Medium | High
[13 empty] | Gates Score | 65 - 70 | 71 - 80 | 80 - 100
Release Number | <PM to update> | [12 empty] | 50 - 65 | 60 - 70 | 70 - 80 | Requires Risks to be well defined with mitigation action plan in place for the Release
Table 3 | <PMs to use this table to derive the Risk Category for the release by selecting the Assessment scale for each Risk Factor under consideration> | [12 empty] | <50 | <60 | <70 | Requires Exception Approval from Sody and Arnaud
RISK ASSESSMENT SECTION
Business and Functional Release | [7 empty] | Size (in SPs) | No of Services/Policies | Complexity of Change | Deployment complexity | Opernational, ProductUpgrde | Risk Score
Factors | Assessment<PM to update> | Risk Score | [5 empty] | Scale | Scale | Scale | Scale |  | Scale | Score
Size (in SPs) | Medium (21-40) | 2 | [5 empty] | Small (0-20) |  |  |  |  | High | 3
No of Services/Policies | Medium (3 - 6) | 2 | [6 empty] | Small (0 - 2) |  |  |  | Huge (>100) | 4
Complexity of Change | Medium | 2 | [7 empty] | Low | Low | Low | Large ( >6 ) | 3
Impact on Consumers | Medium | 2 | [5 empty] | Medium (21-40) |  |  |  |  | Large (41-100) | 3
Complexity of UAT/QA Testing | Medium | 2 | [6 empty] | Medium (3 - 6) |  |  |  | Low | 1
Deployment complexity (rollback, external testing, unknowns) | Low | 1 | [7 empty] | Medium |  | Medium | Medium | 2
Operational Maintenance complexity (housekeeping, monitoring/alerts, cert upgrade, etc) | Low | 1 | [5 empty] | Large (41-100) |  |  |  |  | Medium (21-40) | 2
Product upgrade complexity (L7, Tibco, Couchbase, Kaazing, etc) | NA | 0 | [6 empty] | Large ( >6 ) |  |  |  | Medium (3 - 6) | 2
Total Risk Score |  | 12 | [7 empty] | High | High | High | Small (0 - 2) | 1
[8 empty] | Huge (>100) |  |  |  |  | Small (0-20) | 1
[8 empty] | NA | NA |  |  | NA | NA | 0
RISK ASSESSMENT | MEDIUM | <derived from Table 2 based on Total Risk Score>
WARNING | None
[13 empty] | Risk Category | Risk Score
Table 4 | <This table provides the evaluated Gates Score for the release components> | [11 empty] | LOW | 1 - 5
GATES ASSESSMENT SECTION | [12 empty] | MEDIUM | 6 - 12
[13 empty] | HIGH | 13 - 25
Revised Checklist v3
EIS service weight |  | 18 | 14 | 16 | 14 | 10
API policy weight |  | 25 | 8 | 15 | 17 | 8
Release |  | Requirements and Planning [DxG0] | Design [DxG1] | Build [DxG2] | Testing [DxG3] | Release readiness [DxG4] | GATES SCORE
<PM to update> |  | 0% | 0% | 0% | 0% | 6.25% | 6.25%
APICustomerGateway |  | 0 | 0 | 0 | 0 | 0
R26-PostAuth |  | 0 | 0 | 0 | 0 | 0.625
SSss
x
TOTAL GATES SCORE | 6.25% | <derived from Table 4>

## EIS_Checklist_<APICustomerGatew (hidden)
Operational instructions: There should be one checklist for each service or policy This will be based on user stories planned in a sprint or project phasewise requirements defined in project plan The checklist should be prepared/updated by the DxM or PM and shared as a google drive sheet The Gates DxG0 to DxG3 should be Reviwed and Approved 1 week ahead of the Planned Release date The Gates DxG4 should be Reviewed and Approved atleast 2 working days in advance to the Planned Release date The Go/NoGo to be planned with All Key stakeholders prior to the Release in discussion with the SQM
| Description | Weight | Applicable YES/NO | Guidelines for Artefact/evidence to be provided | Artefact location link or url | Gate Review Date <DDMMYY> | Gate Status [1-Approved, 0-Rejected] | Remark
| REQUIREMENT AND PLANNING |  | <to be added by DxM / PM and agreed with SQM> |  | <to be added by DxM / PM> | <to be added by DxM / PM> | <To be done by SQM> | <to be added by DxM / PM>
1 | Business and System Requirements mapping matrix | 0.055556 | No | Requirement document for projects (including enhancement). Jira user stories/epic reference for Dx service enhancements. | No separate doc, part of Requirements statement
2 | Requirements statement | 0.055556 | Yes | https://tools.ladbrokes.com/confluence/display/SS/API+Streamline | https://tools.ladbrokes.com/confluence/display/SS/API+Streamline |  |  | Jira User story for EIS Manageed ServicesSprint 31-36 SOW for burst projects
3 | Added Matrix for list of Impacted systems- Internal ladbrokes systems, external systems, 3rd party systems | 0.055556 | Yes | Requirement document for projects (including enhancement). Jira user stories/epic reference for Dx service enhancements. | https://tools.ladbrokes.com/confluence/display/SS/API+Streamline |  |  | <SK> this should be the list of impacted partners? refer to partner usage list! https://docs.google.com/spreadsheets/d/1MGHGITZkHqG556a1eX8XN1uQchowBRUnnoAXLnJDer8/edit#gid=2063533688
| Operational requirements Captured and recorded |  |  | Requirement document for projects (including enhancement). Jira user stories/epic reference for Dx service enhancements. | http://10.32.18.100/svn/eis/AnalysisDesign/ComponentDesign/Technical/API/APICustomerGateway/HLSD/APICustomerGateway 1.0 HLSD v0.1.docx |  |  | Service is already operation
4 | NFRs | 0.055556 | NA | For existing /live services indicate the location where this is defined. For new services, indicate the requirement document defining this component.
5 | Volumetrics | 0.055556 | NA | same as above
6 | Monitoring and alerts | 0.055556 | NA | same as above |  |  |  | Service is already operation with all relevant checks - RAG,Kibana
7 | Achiving, housekeeping | 0.055556 | NA | same as above |  |  |  | Service is already operation with all relevant checks - RAG,Kibana
8 | Configuration setup changes - prod and nonprod | 0.055556 | NA | same as above | CHG0040291
| Previous P1/P2s in PROD analysed and considered as requirements |  | Yes | Requirement document for projects (including enhancement). Jira user stories/epic reference for Dx service enhancements. | https://drive.google.com/drive/folders/0B4pIWUeMWeWIZG1jM2IzblNOaUE
9 | Specific Test requirements | 0.055556 | NA |  | https://drive.google.com/drive/u/0/folders/0B2-yjVmEzv9efjFJekJQaklYNTE2NU9JbndvU0R3bkZCQkd2eGM1Qk94bnVvVGdVZE9jNms |  |  | To test the PostAuth Policies through Gateway using HTTP
| Solution paper |  | NA
10 | Impact assessment | 0.055556 | NA
11 | Hligh level/ ballpark Estimation | 0.055556 | NA
12 | List of Candidate Business Services | 0.055556 | Yes |  | APICustomerGateway
13 | Assumption and Dependencies listed | 0.055556 | Yes |  | http://10.32.18.100/svn/eis/docs/AnalysisDesign/ComponentDesign/Technical/API/APICustomerGateway/SCD/APICustomerGateway 1.0 SCD v0.1.docx |  |  | Enhanced Gateway service implemented There is no EA model, provide the SCD link
| High Level Project plan |  | Yes |  | https://docs.google.com/spreadsheets/d/1BP0524ce_m43TFRWFyltAEjEAPug_DrxQlPxUQlckmE/edit#gid=1319981748 https://docs.google.com/spreadsheets/d/1flQ4SlIePS1emymG_kDcb2kNVZduiv9vrOgIUz59INI/edit?ts=568f5f29#gid=925564529
14 | Project planned | 0.055556 | Yes
15 | Project, SOW approved | 0.055556 | Yes |  | Streamlining SOW
16 | Resource allocated | 0.055556 | Yes
17 | RAID updated | 0.055556 | Yes
18 | Project go-ahead from business stakeholders | 0.055556 | Yes |  | SOW signed off
| Requirements and Planning checklist [DxG0] | 1 | 11 |  |  |  | 0
ARCHITECTURE & SOLUTIONING & DESIGN
1 | Review Candidate Service in Architecture Gov board (AGB) | 0.071429 | NA |  |  |  |  | EIS-866 (Old US)
2 | Update Solution Architect Document(PROJECT)/ Design guidance document | 0.071429 | NA |  |  |  |  | EIS-866 (Old US)
3 | Approve Candidate Service in Architecture Gov board / Lead architect (as applicable) | 0.071429 | NA |  |  |  |  | EIS-866 (Old US)
4 | Create HL Solution Design (HLSD) - ONLY FOR PROJECTS | 0.071429 | Yes |  | http://10.32.18.100/svn/eis/AnalysisDesign/ComponentDesign/Technical/API/APICustomerGateway/HLSD/APICustomerGateway 1.0 HLSD v0.1.docx |  |  | No update required for Prod issues observed
5 | Requirements mapped to solution in HLSD or Design Guidance document | 0.071429 | Yes |  | EIS-1207,EIS-1299 |  |  | No update required for Prod issues observed
6 | Review and Approve HLSD - ONLY FOR PROJECTS | 0.071429 | NA |  | EIS-1207,EIS-1299 |  |  | No update required for Prod issues observed
7 | Plan updated | 0.071429 | Yes |  | EIS-1207,EIS-1299 |  |  | plan reqd
8 | Create Service Contract Document (SCD) as applicable | 0.071429 | NA |  | http://10.32.18.100/svn/eis/AnalysisDesign/ComponentDesign/Technical/API/APICustomerGateway/SCD/APICustomerGateway 1.0 SCD v0.1.docx |  |  | No update required for Prod issues observed
9 | Review and Approve SCD as applicable | 0.071429 | NO
10 | Design walkthrough organised and conducted | 0.071429 | NA |  |  |  |  | Enhanced Gateway service implemented hence walkthrough was not initiated No update required for Prod issues observed
11 | Review and Approve Contract Request and SLA | 0.071429 | NA
12 | Service Categorisation updated - Data sheet updated | 0.071429 | NA |  |  |  |  | Enhanced Gateway service implemented
13 | Service Change tracker created/updated | 0.071429 | Yes |  |  |  |  | Serivces are updated in Service change Tracker list
14 | Project plan and RAID updated | 0.071429 | Yes |  | Row 20
| Design Checklist [DxG1] | 1 | 5 |  |  |  | 0
INTEGRATION & IMPLEMENTATION & BUILD
1 | Service/s implemented | 0.0625 | Yes |  | http://10.32.18.100/svn/eis/trunk/Development/Code/Bw/Technical/API/APICustomerGateway/1.0/APICustomerGateway
2 | Coding standards followed | 0.0625 | Yes |  | http://10.32.18.100/svn/docs/ProcessManagement/StandardsProcesses\Standards |  |  | <add the link for standards followed>
3 | Services code reviewed | 0.0625 | Yes |  | DX-482, DX-739, DX-689, EIS-1329, DX-840http://10.32.18.100/svn/eis/docs/ProjectManagement/Reviews/Agile/Sprint36/APICustomerGateway_Code_Review.xlsx |  |  | Satya reviewed the code changes , avaiable in the Review log
4 | UTCs defined and reviewed | 0.0625 | Yes |  | DX-482, DX-739, DX-689, EIS-1371 , EIS-1329 , EIS-1301 ,EIS-1254, EIS-1129 , DX-840 http://10.32.18.100/svn/eis/AnalysisDesign/ComponentDesign/Technical/API/APICustomerGateway/UTC/Unit Test Cases - APICustomergateWay.xlsx |  |  | In Test cases , it has been place Satya reviewd the test cases and result
5 | CQM process for code version control - SVN followed | 0.0625 | Yes |  | http://10.33.20.7:8080/artifactory/webapp/browserepo.html?0 EIS_DEVOPS - > DX-20 |  |  | Dev Ops process - RC has been created
6 | Code quality analysis using Sonar done and changes implemented | 0.0625 | NA |  |  |  |  | SONAR not implemented for EIS
7 | Code merger implemented (as applicable across parallel projects) | 0.0625 | NA |  |  |  |  | No Parallel Branches required
8 | Service/s Unit Tested | 0.0625 | Yes |  | DX-482, DX-739, DX-689, EIS-1371 , EIS-1329 , EIS-1301 ,EIS-1254, EIS-1129 http://10.32.18.100/svn/eis/AnalysisDesign/ComponentDesign/Technical/API/APICustomerGateway/UTC/Unit Test Cases - APICustomergateWay.xlsx |  |  | UTC's are included in SVN
9 | Services unit test results reviewed | 0.0625 | Yes |  | DX-482, DX-739, DX-689, EIS-1371 , EIS-1329 , EIS-1301 ,EIS-1254, EIS-1129 http://10.32.18.100/svn/eis/AnalysisDesign/ComponentDesign/Technical/API/APICustomerGateway/UTC/Unit Test Cases - APICustomergateWay.xlsx
10 | Service/s Performance tested for NFR | 0.0625 | Yes |  | https://docs.google.com/spreadsheets/d/1wCpOFLRDhyXIJlwhN9EnBQmWXTjDQ17Z0wgKmtBrXbQ/edit?ts=560c262f#gid=652928202 |  |  | To be done as part of API perf runs
11 | Services Perf test results reviewed | 0.0625 | Yes |  | https://docs.google.com/spreadsheets/d/1qlGwE27O20Ng6APKkuzcnMFTbe1KqnO6gnQZ8xw1Kj0/edit#gid=258038104
12 | Automated Build followed along with Unit testing | 0.0625 | Yes |  | http://10.33.20.7:8080/artifactory/webapp/browserepo.html?0 EIS_DEVOPS - > DX-20 |  |  | Devops Model followed
13 | Regression pack updated | 0.0625 | Yes |  | http:\\10.32.18.100\svn\trunk\Development\Testing\Regression\Scripts\APICustomerGateway.jmx
14 | Automated Deployment followed along with automated testing | 0.0625 | Yes |  | http://10.33.20.7:8080/artifactory/webapp/browserepo.html?0 EIS_DEVOPS - > DX-20 |  |  | Automated testing cannot be done as there is connectivity issue from Jenkins to Regression pack, Raised Service now ticket
15 | Release pack created in LSG | 0.0625 | Yes |  | http://10.33.20.7:8080/artifactory/webapp/browserepo.html?0 EIS_DEVOPS - > DX-20 |  |  | Dev Ops process - RC has been created
16 | Project plan and RAID updated | 0.0625 | Yes |  | Row 20
| Build Checklist [DxG2] | 1 | 14 |  |  |  | 0
QA TESTING
1 | Environment configuration change implemented and validated | 0.071429 | NA
2 | QA functional TCs reviewed | 0.071429 | Yes |  | EIS-1301, DX-482 , DX-739 http://10.32.18.100/svn/trunk/Development\Testing\QA-Report\APIGateWay\APICustomerGateway1.0.xlsx
3 | Deployment in UAT environment | 0.071429 | Yes |  | http://10.33.20.7:8080/artifactory/webapp/browserepo.html?0 EIS_DEVOPS - > RC_APIBettingGateway
4 | Test data readiness for UAT/Stage testing | 0.071429 | NA
5 | Test execution in UAT/Stage environment | 0.071429 | Yes |  | EIS-1301, DX-482 , DX-739 http://10.32.18.100/svn/trunk/Development\Testing\QA-Report\APIGateWay\APICustomerGateway1.0.xlsx
6 | Defect list available with status updated | 0.071429 | Yes |  | DX-739
7 | Test data readiness for PERF testing | 0.071429 | NA
8 | CIP scripts PERF updated | 0.071429 | No |  |  |  |  | Customer GW will be added in the CIP scripts,
9 | Load Test and NFR test execution in PERF environment | 0.071429 | No |  |  |  |  | Customer GW will be added in the CIP scripts,
10 | 3rd party systems integration, Internal Ladbrokes system and External ladbrokes system tested | 0.071429 | Yes |  | API and its Partners
11 | NFRs achieved | 0.071429 | NA |  | https://docs.google.com/spreadsheets/d/1qlGwE27O20Ng6APKkuzcnMFTbe1KqnO6gnQZ8xw1Kj0/edit#gid=258038104
12 | Operational requirements tested and met | 0.071429 | NA
| Previous P1-P2s in PROD scenarios tested |  | NA |  | Part of test scenarios
13 | QA test sign-off with Test completion report | 0.071429 | Yes
14 | Project plan and RAID updated | 0.071429 |  | Evidence of updated plans - sheet, Jira user stories, etc and RAID register updates | Refer Row 20
| Testing Checklist [DxG3] | 1 | 6 |  |  |  | 0
RELEASE Readiness
1 | Version reference on Jira created/updated | 0.1 | Yes | Version reference in Jira for Release and linked to ALL US's associated CQM build reference for production deployment | DX-20
2 | Service Categorisation updated - Servers updated | 0.1 | Yes | Link and evidence of updates | https://tools.ladbrokes.com/confluence/display/DX/EIS+Service+Categorisation
3 | Release plan updated | 0.1 | Yes | Deployment plan with resource names, Sequence of activities, Comms included throughout release window | https://tools.ladbrokes.com/confluence/display/DX/Release+Notes+-+DX-20
4 | Programe RAID updated | 0.1 | Yes | Evidence of updated RAID register in Release register workbook | https://tools.ladbrokes.com/confluence/display/DX/Release+Notes+-+DX-20
5 | Release notes | 0.1 | Yes | Document made available for CAB uploaded on change | https://tools.ladbrokes.com/confluence/display/DX/Release+Notes+-+DX-20
6 | Runbook (implementation, backout plan) | 0.1 | Yes | Document made available for CAB uploaded on change | https://docs.google.com/spreadsheets/d/1voaUyFf-2hRiJ61iZc6DvVw0acfLOGVj7kl2ag3jiDc/edit#gid=0
7 | CAB CR submitted, reviewed and approved | 0.1 | Yes | CAB CR reference | CHG0040291
8 | Other affected streams, 3rd Party informed about release | 0.1 | Yes | email evidence informing all impacted stakeholders internal and external about the planned release | API Partners |  |  | will be informed on Monday
9 | IT Sprint update | 0.1 | Yes |  | https://docs.google.com/spreadsheets/d/1x9pQm6pKFKv78PLPQZF2kSBnwXu2eBLYM5GeBRw9uLc/edit#gid=0
10 | KT and knowledge transition to L2/L3 support team | 0.1 | Yes | Confirmation mail from Support about completion of KT |  |  |  | will be given post release
| Release readiness GO/NO-GO [DxG4] | 1 | 10 |  |  |  | 0
RELEASE deployment & validation
1 | Deployment in PRODUCTION | 0.125 |  | Regular Comms from deployment team throughout the release window
2 | Deployment in PrePROD as DR | 0.125 |  | Comms from deployment team
3 | Post release Testing completed | 0.125 |  | Comms from deployment team
4 | Post release Issue tracker updated | 0.125 |  | Confirmation of update to Sheet in Release register
5 | Release activities completed | 0.125 |  | Comms from deployment team
6 | IT Sprint update | 0.125 |  | Confirmation of update
7 | Production live Issues tracker updated | 0.125 |  | Confirmation of update to Sheet in Release register
8 | Release retrospective and lessons learnt updated | 0.125 |  | Confirmation of update to Sheet in Release register
| Project /Release Closure | 1 |  |  |  |  | 0

## API_Checklist_<PostAuth R26>OLD (hidden)
Operational instructions: There should be one checklist for each service or policy This will be based on user stories planned in a sprint or project phasewise requirements defined in project plan The checklist should be prepared/updated by the DxM or PM and shared as a google drive sheet The Gates DxG0 to DxG3 should be Reviwed and Approved 1 week ahead of the Planned Release date The Gates DxG4 should be Reviewed and Approved atleast 2 working days in advance to the Planned Release date The Go/NoGo to be planned with All Key stakeholders prior to the Release in discussion with the SQM
| Description | Weight | Applicable YES/NO | Artefact location link or url | Gate Review Date <DDMMYY> | Gate Status [1-Approved, 0-Rejected] | Remark (Mandatory if Aoplicable is NO)
| REQUIREMENT AND PLANNING |  | <to be added by DxM / PM and agreed with SQM> | <to be added by DxM / PM> | <to be added by DxM / PM> | <To be done by SQM> | <to be added by DxM / PM>
1 | Partner/Affiliate onboarding | 0.04 | NO |  |  |  | This is a technical initiative
2 | Requirment and user journey captured | 0.04 | Yes | https://tools.ladbrokes.com/confluence/display/SS/API+Streamline |  |  | This is a technical initiative
3 | API key provided | 0.04 | NO |  |  |  | This is a technical initiative Support team has configured the http policies for the new partners,
4 | Business Client/Partner Requirements captured | 0.04 | NO |  |  |  | This is a technical initiative
5 | Requirements statement | 0.04 | Yes | https://tools.ladbrokes.com/confluence/display/SS/API+Streamline API 1746
6 | Added Matrix for list of Impacted systems- Internal ladbrokes systems, external systems, 3rd party systems | 0.04 | Yes | https://tools.ladbrokes.com/confluence/display/SS/API+Streamline
| Operational requirements Captured and recorded |  | NO |  |  |  | Same operational API changes are applicable
7 | NFRs | 0.04 | NO
8 | Volumetrics | 0.04 | NO
9 | Monitoring and alerts | 0.04 | NO
10 | Achiving, housekeeping | 0.04 | NO
11 | Configuration setup changes - prod and nonprod | 0.04 | No
12 | Security requirements |  | NO
13 | API solution analysis | 0.04 | Yes | https://tools.ladbrokes.com/confluence/display/SS/API+Streamline
14 | EIS solution analysis | 0.04 | Yes | https://tools.ladbrokes.com/confluence/display/SS/API+Streamline
15 | Feasibility analysis/ Proof of Concept done | 0.04 | Yes | https://tools.ladbrokes.com/confluence/display/SS/API+Streamline
16 | Specific Test requirements considered | 0.04 | Yes | https://drive.google.com/drive/u/0/folders/0B2-yjVmEzv9efjFJekJQaklYNTE2NU9JbndvU0R3bkZCQkd2eGM1Qk94bnVvVGdVZE9jNms |  |  | refer - API STREAMLINING-For Tibco-Customer Gateway.docx
| Solution brief documented |  | Yes | https://tools.ladbrokes.com/confluence/display/SS/API+Streamline
17 | Impact assessment | 0.04 | Yes | https://drive.google.com/drive/u/0/folders/0B2-yjVmEzv9efjFJekJQaklYNTE2NU9JbndvU0R3bkZCQkd2eGM1Qk94bnVvVGdVZE9jNms |  |  | refer - API STREAMLINING-For Tibco-Customer Gateway.docx
18 | Hligh level/ ballpark Estimation | 0.04 | Yes | API-1746, API-1819, API-1852, API -1860
19 | List of Candidate Business Services/policies | 0.04 | Yes | R26-Post Auth Selection Instance V2 - JMS Error Code configuration changes
20 | Assumption and Dependencies listed | 0.04 | Yes | https://docs.google.com/spreadsheets/d/1qlGwE27O20Ng6APKkuzcnMFTbe1KqnO6gnQZ8xw1Kj0/edit#gid=2055130554
| High Level Project plan |  | Yes | API-1746, API-1819, API-1852, API -1860 , DX-75, DX-240, https://docs.google.com/spreadsheets/d/1BP0524ce_m43TFRWFyltAEjEAPug_DrxQlPxUQlckmE/edit#gid=1319981748 https://docs.google.com/spreadsheets/d/11RaV2yiMYY6NlVug8HTM1cZ-mE3clGSNEsd9NePJ48c/edit?ts=56fb73be#gid=692339785
21 | Project planned | 0.04 | Yes
22 | Project, SOW approved | 0.04 | Yes | taken in Managed services
23 | Resource allocated | 0.04 | Yes
24 | RAID updated | 0.04 | Yes | updated in RAID in Release Register
25 | Project go-ahead from Ladbrokes business stakeholders | 0.04 | Yes | SOW signed off
| Requirements and Planning checklist [DxG0] |  |  |  |  | 0
ARCHITECTURE / SOLUTIONING
1 | Design Guidance document created | 0.125 | Yes | https://docs.google.com/document/d/1ymKQZbdj-s1f4lF1NTLebxuuJZPehWSS-1MFNR7Q_fQ/edit
2 | Requirements mapped to Solution brief and Design guidance | 0.125 | Yes | https://docs.google.com/document/d/1ymKQZbdj-s1f4lF1NTLebxuuJZPehWSS-1MFNR7Q_fQ/edit
3 | Design Guidance document reviewed | 0.125 | Yes | Walk through session with the team and Stake holders
4 | EIS solution agreed and EIS process followed | 0.125 | Yes | Walk through session with the EIS team and architect
5 | Update Solution Architect Document (as applicable) | 0.125 | Yes | Developer manual updated
6 | Approve Candidate Service in Architecture Gov board (AGB) | 0.125 | Yes |  |  |  | The solution was discussed and approved from Arnaud based on the POC
7 | Design walkthrough organised and conducted | 0.125 | Yes | Walk through session with the team and Stake holders
8 | Project plan and RAID updated | 0.125 | Yes | Refer Row 26
| Design Checklist [DxG1] |  |  |  |  | 0
INTEGRATION and BUILD
1 | Layer7 policies creation/modification implemented | 0.066667 | Yes | Present in Policy Manager
2 | Webforms created/modified | 0.066667 | NA |  |  |  | Not in scope
3 | Coding standards followed | 0.066667 | Yes | https://drive.google.com/drive/u/0/folders/0B6bJ2Y5priFWUzRYckNjLXdGRGM
4 | Code reviewed | 0.066667 | Yes | API-1746, API-1819, API-1915, API-1852, API -1860 , DX-75, DX-240,
5 | UTCs defined and reviewed | 0.066667 | Yes | https://drive.google.com/drive/folders/0B5njbiluODhnV1dJejlqdXA0VzA
6 | CQM process for code version control - SVN followed | 0.066667 | NA |  |  |  | Not setup for Layer 7 policies
7 | Code quality analysis using Sonar done and changes implemented | 0.066667 | NA
8 | Unit Testing completed | 0.066667 | Yes | API-1746, API-1819, API-1915, API-1852, API -1860 , DX-75, DX-240
9 | Unit test results reviewed | 0.066667 | Yes | API-1746, API-1819, API-1915, API-1852, API -1860 , DX-75, DX-240
10 | Automated Build followed including automated Unit testing | 0.066667 | NA |  |  |  | Not setup for Layer 7 policies
11 | Regression pack updated | 0.066667 | No | DX-49,DX-240,DX-386,DX-299,DX-512, |  |  | Regression pack is updated for all the Betting policies Regression pack automation for the partner usage in Betting module will be taken BAU
12 | Automated Deployment followed including automated testing followed in non-prod environments | 0.066667 | NA | Not required, Its URL switch
13 | Release pack created | 0.066667 | NA
14 | Developer Manual updated | 0.066667 | Yes | Vamshee is in process of update will share with you on monday
15 | Project plan and RAID updated | 0.066667 | Yes | Refer Row - 26
| Build Checklist [DxG2] |  |  |  |  | 0
TESTING
1 | Environment configuration change implemented and validated | 0.055556 | No |  |  |  | There is no env change
2 | QA functional TCs reviewed | 0.055556 | Yes | DX-708 , DX-838
3 | CIP scripts for UAT updated | 0.055556 | Yes | DX-49,DX-240,DX-386,DX-299,DX-512,DX-365
4 | Deployment in UAT environment | 0.055556 | Yes |  |  |  | No Build reference : SVN is not used for the deployment, so no reference number
5 | Test data readiness for UAT/Stage testing | 0.055556 | Yes |  |  |  | While doing partner usage testing prepared test data
6 | Test execution in UAT/Stage environment | 0.055556 | Yes |  |  |  | evidence : QA test results
7 | Defect list available with status updated | 0.055556 | Yes | https://drive.google.com/drive/folders/0B4pIWUeMWeWIZG1jM2IzblNOaUE API-1970, API-1969, API-1982, API-1983
8 | Environment setup and Test data readiness for PERF testing | 0.055556 | Yes
9 | Sandbox environment setup with APP test builds | 0.055556 | Yes | Tested with Racing post and onionsack apps |  |  | <evidence?> https://drive.google.com/drive/folders/0B5njbiluODhnV1dJejlqdXA0VzA
10 | CIP scripts for PERF updated | 0.055556 | Yes | DX-49,DX-240,DX-386,DX-299,DX-512, https://docs.google.com/spreadsheets/d/1qlGwE27O20Ng6APKkuzcnMFTbe1KqnO6gnQZ8xw1Kj0/edit#gid=1206994564 |  |  | <evidence?> Present in CIP box, Daily CIP runs on Perf env is done on the http ploicies, the same report is shared with Arnaud
11 | Load Test and NFR test execution in PERF environment | 0.055556 | Yes | https://docs.google.com/spreadsheets/d/1qlGwE27O20Ng6APKkuzcnMFTbe1KqnO6gnQZ8xw1Kj0/edit#gid=258038104
12 | 3rd party systems integration (incl APPs) , Internal Ladbrokes system and External ladbrokes system tested | 0.055556 | Yes | https://docs.google.com/spreadsheets/d/16DkrMs1RjxvrTiGZvf70FdYNAzp2mEa6IhdGIKe05MA/edit#gid=1917400909
13 | NFRs achieved | 0.055556 | Yes | https://docs.google.com/spreadsheets/d/1qlGwE27O20Ng6APKkuzcnMFTbe1KqnO6gnQZ8xw1Kj0/edit#gid=258038104 |  |  | <checkbetslip v1 and v2 load runs tbc on Mon> MV : As discussed in the call, with low TPS JMS versions has better perfomenace than http, However we see good perfomenace for higher TPS which is a real time scenario. As discussed further in the call , another round of performance runs will be done post prod release
14 | Operational requirements tested and met | 0.055556 | Yes
15 | App testing and 3rd party system integration testing | 0.055556 | Yes | https://docs.google.com/spreadsheets/d/16DkrMs1RjxvrTiGZvf70FdYNAzp2mEa6IhdGIKe05MA/edit#gid=1917400909 https://docs.google.com/spreadsheets/d/1MGHGITZkHqG556a1eX8XN1uQchowBRUnnoAXLnJDer8/edit#gid=2063533688
16 | QA test sign-off with Test completion report | 0.055556 | Yes | https://docs.google.com/spreadsheets/d/1vFIA26Crg2cXGi05PX6iAXqIx_kXCXfcPePeDxA4Cfs/edit#gid=503350188https://docs.google.com/document/d/1xybsykXqw4pQ7ykLg_4f32kiEHOqZ5G92S-JYsn_4L8/edit |  |  | <QA test exit report> Will share it tomorrow
17 | Security test sign-off report | 0.055556 | NA
18 | Project plan and RAID updated | 0.055556 | NA | Taken up in Sprints
| Testing Checklist [DxG3] |  |  |  |  | 0
RELEASE Readiness
1 | Version reference on Jira created/updated | 0.125 | Yes | DX-20 |  | 1
2 | Release plan updated | 0.125 | Yes | https://tools.ladbrokes.com/confluence/display/DX/EIS+Service+Categorisation |  | 1
3 | Programe RAID updated | 0.125 | Yes | https://tools.ladbrokes.com/confluence/display/DX/Release+Notes+-+DX-20 |  | 1
4 | Release notes | 0.125 | Yes | https://tools.ladbrokes.com/confluence/display/DX/Release+Notes+-+DX-20 |  | 0
5 | Runbook (implementation, backout plan) | 0.125 | Yes | https://tools.ladbrokes.com/confluence/display/DX/Release+Notes+-+DX-20 |  | 0
6 | CAB CR submitted, reviewed and approved | 0.125 | Yes | https://docs.google.com/spreadsheets/d/1voaUyFf-2hRiJ61iZc6DvVw0acfLOGVj7kl2ag3jiDc/edit#gid=0 |  | 0
7 | Other affected streams, 3rd Party informed about release | 0.125 | Yes | CHG0040291 |  | 1
8 | KT and knowledge transition to L2/L3 support team | 0.125 | Yes | API Partners |  | 1
| Release readiness GO/NO-GO [DxG4] |  |  |  |  | 5
RELEASE deployment & validation
1 | Deployment in PRODUCTION | 0.14286 |  |  |  | 1
2 | Deployment in PrePROD | 0.14286 |  |  |  | 0
3 | Post release Testing completed | 0.14286 |  |  |  | 1
4 | Post release Issue tracker updated | 0.14286 |  |  |  | 1
5 | Release activities completed | 0.14286 |  |  |  | 0
6 | Production Issues tracker updated | 0.14286 |  |  |  | 0
7 | Release retrospective and lessons learnt updated | 0.14286 |  |  |  | 1
| Project Closure |  |  |  |  | 4

## EIS_Checklist_<Alibaba Integrat (hidden)
Operational instructions: There should be one checklist for each service or policy This will be based on user stories planned in a sprint or project phasewise requirements defined in project plan The checklist should be prepared/updated by the DxM or PM and shared as a google drive sheet The Gates DxG0 to DxG3 should be Reviwed and Approved 1 week ahead of the Planned Release date The Gates DxG4 should be Reviewed and Approved atleast 2 working days in advance to the Planned Release date The Go/NoGo to be planned with All Key stakeholders prior to the Release in discussion with the SQM
| Description | Weight | Applicable YES/NO | Guidelines for Artefact/evidence to be provided | Artefact location link or url | Gate Review Date <DDMMYY> | Gate Status [1-Approved, 0-Rejected] | Remark
| REQUIREMENT AND PLANNING |  | <to be added by DxM / PM and agreed with SQM> |  | <to be added by DxM / PM> | <to be added by DxM / PM> | <To be done by SQM> | <to be added by DxM / PM>
| Business and System Requirements mapping matrix | 0.055556 | Yes |  | DX-1158 |  |  | <SK>: Provide the user stories whcih Arnaud had defined as well
2 | Requirements statement | 0.055556 | Yes |  | DX-1158 |  |  | Requirements discussed with the client by the Onshore coordinator
3 | Added Matrix for list of Impacted systems- Internal ladbrokes systems, external systems, 3rd party systems | 0.055556 | NA
| Operational requirements Captured and recorded |  | NA
4 | NFRs | 0.055556 | NA | For existing /live services indicate the specific location, link and section where this is defined. For new services, indicate the requirement document defining this component.
5 | Volumetrics | 0.055556 | NA | same as above
6 | Monitoring and alerts | 0.055556 | NA | same as above
7 | Achiving, housekeeping | 0.055556 | NA | same as above
8 | Configuration setup changes - prod and nonprod | 0.055556 | NA | same as above
| Previous P1/P2s in PROD analysed and considered as requirements |  | NA
9 | Specific Test requirements | 0.055556 | NA | Requirements should indicate if there are any specific tests which need to be completed Requirement document for projects (including enhancement). Jira user stories/epic reference for Dx service enhancements. | DX-1158
| Solution paper |  | NA | Below sections apply to All requirements: small to large. For projects, if there is a document created, require reference to it. If these are in Jira Would like to see evidence of the US's/Epics planned to cover the solution proposed.
10 | Impact assessment | 0.055556 | Yes |  | DX-1158
11 | Hligh level/ ballpark Estimation | 0.055556 | Yes |  | DX-1158
12 | List of Candidate Business Services | 0.055556 | Yes |  | APISportsbookGateway SiteServerWrapperService CouchbaseSportsbookReader Kaazing Publisher CouchbaseSportsbookWriter OXIReplicationGateway
13 | Assumption and Dependencies listed | 0.055556
| High Level Project plan |  | NA | Below sections apply to All requirements: small to large. For projects, I require a HL Plan reference. If these are planned as Jira would like to see all US's/Epics planned to cover the solution delivery | DX-1158
14 | Project planned | 0.055556 | NA |  | DX-1158
15 | Project, SOW approved | 0.055556 | NA
16 | Resource allocated | 0.055556 | Yes
17 | RAID updated | 0.055556 | NA |  |  |  |  | No RAID for this change
18 | Project go-ahead from business stakeholders | 0.055556 | Yes | Require an evidence suggesting the requirement scope, proposed solution and HL plan accepted by Business PMs, Product owners, or relevant LBR stakeholders | DX-1158
| Requirements and Planning checklist [DxG0] | 1 | 7 |  |  |  | 0
ARCHITECTURE & SOLUTIONING & DESIGN
1 | Review Candidate Service in Architecture Gov board (AGB) | 0.071429 | Yes | Require evidence of confirmation from Architects with list of review recommendation/comments |  |  |  | No Design change, populating major , minor code for Selection document based on OXIRep data received
2 | Update Solution Architect Document(PROJECT)/ Design guidance document | 0.071429 | NA | Link to document with appropriate version control/history |  |  |  | No changes to SCD or HLSD documents , as there has been no new fields added, only mapping changes in the code
3 | Approve Candidate Service in Architecture Gov board / Lead architect (as applicable) | 0.071429 | Yes | Require evidence of confirmation from Architects |  |  |  | No changes to SCD or HLSD documents , as there has been no new fields added, only mapping changes in the code
4 | Create HL Solution Design (HLSD) - ONLY FOR PROJECTS | 0.071429 | NA | Link to document with appropriate version control/history |  |  |  | No changes to SCD or HLSD documents , as there has been no new fields added, only mapping changes in the code
5 | Requirements mapped to solution in HLSD or Design Guidance document | 0.071429 | Yes | Link to document with appropriate sections indicating requirements mapped from DxG0 |  |  |  | No changes to SCD or HLSD documents , as there has been no new fields added, only mapping changes in the code
6 | Review and Approve HLSD - ONLY FOR PROJECTS | 0.071429 | NA | Require evidence of confirmation from Project Architects
7 | Plan updated | 0.071429 | NA | Evidence of updated plans | Sprint -10 -DX-1158 |  |  | Small changes, no design review required
8 | Create Service Contract Document (SCD) as applicable | 0.071429 | NA | Link to document with appropriate version control/history |  |  |  | NA for SportbookReader and SiteServerwrapper service as they are technical services Updated the SCD for SportsbookGateway, svn link shared in DX-1182
9 | Review and Approve SCD as applicable | 0.071429 | NA | Require evidence with list of review recommendation/comments
10 | Design walkthrough organised and conducted | 0.071429 | NA | Require evidence of walkthrough being done
11 | Review and Approve Contract Request and SLA | 0.071429 | NA | Link to document with appropriate version control/history
12 | Service Categorisation updated - Data sheet updated | 0.071429 | NA | Link to document with appropriate version control/history
13 | Service Change tracker created/updated | 0.071429 | Yes | Link to document with appropriate version control/history | https://docs.google.com/spreadsheets/d/1LLNJYPIgIbH6Xw8joQ0Vo3kJW6She0N91sYTmIm6bdE/edit#gid=0
14 | Project plan and RAID updated | 0.071429 |  | Evidence of updated plans and entries into RAID register as appropriate | Sprint -10 -DX-1158 |  |  | Minor change, no RAID required
| Design Checklist [DxG1] | 1 | 4 |  |  |  | 0
INTEGRATION & IMPLEMENTATION & BUILD
1 | Service/s implemented | 0.0625 | Yes |  | APISportsbookGateway SiteServerWrapperService CouchbaseSportsbookReader Kaazing Publisher CouchbaseSportsbookWriter OXIReplicationGateway
2 | Coding standards followed | 0.0625 | Yes | link to applicable coding standards used for impacted systems | http://10.32.18.100/svn/docs/ProcessManagement/StandardsProcesses/Standards
3 | Services code reviewed | 0.0625 | Yes | Review evidence with appropriate version control/history | DX-1158 |  |  | Information is included in worklog
4 | UTCs defined and reviewed | 0.0625 | Yes | link to list UTCs defined to map to the code changes Review evidence with appropriate version control/history | DX-1158 |  |  | Attached to the Jira story
5 | CQM process for code version control - SVN followed | 0.0625 | Yes | SVN link CQM build reference Reference of Release number in Build |  |  |  | Release candiadate link
6 | Code quality analysis using Sonar done and changes implemented | 0.0625 | NA | As applicable - If EIS analysis is available then should be used
7 | Code merger implemented (as applicable across parallel projects) | 0.0625 | NA | SVN link CQM build reference Reference of Release number in Build
8 | Service/s Unit Tested | 0.0625 | Yes | UTC execution evidence with results | DX-1158
9 | Services unit test results reviewed | 0.0625 | Yes | UTC execution evidence with results | DX-1158
10 | Service/s Performance tested for NFR | 0.0625 | NA | Service/policy level perf testing to ensure this is achieved. Evidence of run/s for NFR defined in DxG0
11 | Services Perf test results reviewed | 0.0625 | NA | Service/policy level perf testing to ensure this is achieved. Evidence of run/s for NFR defined in DxG0
12 | Automated Build followed along with Unit testing | 0.0625 | yes | CQM build reference Evidence of UT execution post deployment to next environment Reference of Release number in Build
13 | Regression pack updated | 0.0625 | Yes | Evidence of List of scripts updated as applicable | http://10.32.18.100/svn/eis/trunk/Development/Testing/Regression/Scripts
14 | Automated Deployment followed along with automated testing | 0.0625 | Yes | CQM build reference Evidence of automated UT execution post deployment to next environment Reference of Release number in Build
15 | Release pack created in LSG | 0.0625 | Yes | Link to LSG |  |  |  | Duplicate entry
16 | Project plan and RAID updated | 0.0625 |  | Evidence of updated plans - sheet, Jira user stories, etc | DX-1158 |  | 1
| Build Checklist [DxG2] | 1 | 11 |  |  |  | 1
QA TESTING
1 | Environment configuration change implemented and validated | 0.071429 | NA | Evidence of environment changes captured when different to Production env
2 | QA functional TCs reviewed | 0.071429 | Yes | Test design, List of TCs , link to TCs Review evidence with appropriate version control/history | DX-1158
3 | Deployment in UAT environment | 0.071429 | Yes | CQM build reference Evidence of Regression test execution post deployment to UAT environment Reference of Release number in Build
4 | Test data readiness for UAT/Stage testing | 0.071429 | Yes | Test data setup confirmation from test team, refering to appropriate data references required for UAT testing | DX-1158
5 | Test execution in UAT/Stage environment | 0.071429 | Yes | Test data setup confirmation from test team, refering to appropriate data references required for UAT testing | DX-1158
6 | Defect list available with status updated | 0.071429 | Yes | Test data setup confirmation from test team, refering to appropriate data references required for UAT testing | DX-1158
7 | Test data readiness for PERF testing | 0.071429 | Yes | Test data setup confirmation from test team, refering to appropriate data references required for UAT testing
8 | CIP scripts PERF updated | 0.071429 | Yes | Link and evidence to updated regression pack |  |  |  | SportsbookGateway is part of CIP runs
9 | Load Test and NFR test execution in PERF environment | 0.071429 | Yes | Evidence of Load test execution and results |  |  |  | SportsbookGateway is part of CIP runs
10 | 3rd party systems integration, Internal Ladbrokes system and External ladbrokes system tested | 0.071429 | Yes | Evidence of test execution and results from All impacted internal and extrenal systems | Testing will be covered for apps using sportsbook API's event/market/selection
11 | NFRs achieved | 0.071429 | Yes | Evidence of Load test execution and results maping to the DxG0
12 | Operational requirements tested and met | 0.071429 | Yes
| Previous P1-P2s in PROD scenarios tested |  | NA | P1-P2s related to the services being delivered to be analysed and Tested. Test evidence to be available.
13 | QA test sign-off with Test completion report | 0.071429 | NA | Test data setup confirmation from test team, refering to appropriate data references required for UAT testing | DX-1158
14 | Project plan and RAID updated | 0.071429 |  | Evidence of updated plans - sheet, Jira user stories, etc and RAID register updates | DX-1158 - Sprint 10
| Testing Checklist [DxG3] | 1 | 11 |  |  |  | 0
RELEASE Readiness
1 | Version reference on Jira created/updated | 0.1 | Yes | Version reference in Jira for Release and linked to ALL US's associated CQM build reference for production deployment
2 | Service Categorisation updated - Servers updated | 0.1 | Yes | Link and evidence of updates
3 | Release plan updated | 0.1 | Yes | Deployment plan with resource names, Sequence of activities, Comms included throughout release window
4 | Programe RAID updated | 0.1 | NA | Evidence of updated RAID register in Release register workbook
5 | Release notes | 0.1 | Yes | Document made available for CAB uploaded on change
6 | Runbook (implementation, backout plan) | 0.1 | Yes | Document made available for CAB uploaded on change
7 | CAB CR submitted, reviewed and approved | 0.1 | Yes | CAB CR reference
8 | Other affected streams, 3rd Party informed about release | 0.1 | Yes | email evidence informing all impacted stakeholders internal and external about the planned release
9 | IT Sprint update | 0.1 | Yes
10 | KT and knowledge transition to L2/L3 support team | 0.1 | Yes | Confirmation mail from Support about completion of KT
| Release readiness GO/NO-GO [DxG4] | 1 | 9 |  |  |  | 0
RELEASE deployment & validation
1 | Deployment in PRODUCTION | 0.125 |  | Regular Comms from deployment team throughout the release window
2 | Deployment in PrePROD as DR | 0.125 |  | Comms from deployment team
3 | Post release Testing completed | 0.125 |  | Comms from deployment team
4 | Post release Issue tracker updated | 0.125 |  | Confirmation of update to Sheet in Release register
5 | Release activities completed | 0.125 |  | Comms from deployment team
6 | IT Sprint update | 0.125 |  | Confirmation of update
7 | Production live Issues tracker updated | 0.125 |  | Confirmation of update to Sheet in Release register
8 | Release retrospective and lessons learnt updated | 0.125 |  | Confirmation of update to Sheet in Release register
| Project /Release Closure | 1 |  |  |  |  | 0

## API_Checklist_<BettingGateway> (hidden)
Operational instructions: There should be one checklist for each service or policy This will be based on user stories planned in a sprint or project phasewise requirements defined in project plan The checklist should be prepared/updated by the DxM or PM and shared as a google drive sheet The Gates DxG0 to DxG3 should be Reviwed and Approved 1 week ahead of the Planned Release date The Gates DxG4 should be Reviewed and Approved atleast 2 working days in advance to the Planned Release date The Go/NoGo to be planned with All Key stakeholders prior to the Release in discussion with the SQM
| Description | Weight | Applicable YES/NO | Artefact location link or url | Gate Review Date <DDMMYY> | Gate Status [1-Approved, 0-Rejected] | Remark (Mandatory if Aoplicable is NO)
| REQUIREMENT AND PLANNING |  | <to be added by DxM / PM and agreed with SQM> | <to be added by DxM / PM> | <to be added by DxM / PM> | <To be done by SQM> | <to be added by DxM / PM>
1 | Partner/Affiliate onboarding | 0.04 | NO |  |  |  | This is a technical initiative
2 | Requirment and user journey captured | 0.04 | Yes | DX-726 |  | 1 | Requirement from the partner to change theerror codes
3 | API key provided | 0.04 | NA |  |  |  | Exsisting API
4 | Business Client/Partner Requirements captured | 0.04 | NO | DX-726 |  |  | This is a technical initiative
5 | Requirements statement | 0.04 | Yes | DX-726 |  | 1
6 | Added Matrix for list of Impacted systems- Internal ladbrokes systems, external systems, 3rd party systems | 0.04 | Yes | DX-726 |  | 1
| Operational requirements Captured and recorded |  | NA
7 | NFRs | 0.04 | NA |  |  |  | Loads run are not executed for JMS versions
8 | Volumetrics | 0.04 | NA |  |  |  | Loads run are not executed for JMS versions
9 | Monitoring and alerts | 0.04 | NA
10 | Achiving, housekeeping | 0.04 | NA
11 | Configuration setup changes - prod and nonprod | 0.04 | NA |  |  |  | Exsisting API
12 | Security requirements |  | NO |  |  |  | Not applicable
13 | API solution analysis | 0.04 | Yes | DX-726 |  | 1
14 | EIS solution analysis | 0.04 | Yes | DX-835 |  | 1
15 | Feasibility analysis/ Proof of Concept done | 0.04 | NA |  |  |  | Exsisting API
16 | Specific Test requirements considered | 0.04 | NA |  |  |  | Exsisting API
| Solution brief documented |  | Yes | DX-726 |  | 1
17 | Impact assessment | 0.04 | NA |  |  |  | Exsisting API, new elements are added
18 | Hligh level/ ballpark Estimation | 0.04 | Yes | DX-726, DX-835, DX-843 |  | 1
19 | List of Candidate Business Services/policies | 0.04 | Yes | BettingGatewayService |  | 1
20 | Assumption and Dependencies listed | 0.04 | Yes | DX-726 |  | 1 | <SK> HAve these added to RAID?
| High Level Project plan |  | Yes | https://docs.google.com/spreadsheets/d/11RaV2yiMYY6NlVug8HTM1cZ-mE3clGSNEsd9NePJ48c/edit?ts=56fb73be#gid=692339785 |  | 1
21 | Project planned | 0.04 | Yes |  |  | 1
22 | Project, SOW approved | 0.04 | Yes | DX-726 |  | 1
23 | Resource allocated | 0.04 | Yes |  |  | 1
24 | RAID updated | 0.04 | Yes | Release notes |  |  | <SK> HAve these added to RAID?
25 | Project go-ahead from Ladbrokes business stakeholders | 0.04 | NA
| Requirements and Planning checklist [DxG0] |  |  |  |  | 13
ARCHITECTURE / SOLUTIONING
1 | Design Guidance document created | 0.125 | Yes | DX-726 |  | 1
2 | Requirements mapped to Solution brief and Design guidance | 0.125 | Yes | DX-726 |  | 1
3 | Design Guidance document reviewed | 0.125 | Yes | DX-726 |  | 1
4 | EIS solution agreed and EIS process followed | 0.125 | NA |  |  |  | Exsisting API, new elements are added
5 | Update Solution Architect Document (as applicable) | 0.125 | Yes | Developer manual updated |  |  | <SK> ref/link
6 | Approve Candidate Service in Architecture Gov board (AGB) | 0.125 | NA |  |  |  | The solution was discussed and approved from Arnaud
7 | Design walkthrough organised and conducted | 0.125 | NA
8 | Project plan and RAID updated | 0.125 | Yes | Refer Row 26 |  |  | <SK>???
| Design Checklist [DxG1] |  |  |  |  | 3
INTEGRATION and BUILD
1 | Layer7 policies creation/modification implemented | 0.066667 | Yes | Present in Policy Manager |  | 1
2 | Webforms created/modified | 0.066667 | NA |  |  |  | Not in scope
3 | Coding standards followed | 0.066667 | Yes | https://drive.google.com/drive/u/0/folders/0B6bJ2Y5priFWUzRYckNjLXdGRGM |  | 1
4 | Code reviewed | 0.066667 | Yes | DX-726 |  | 1
5 | UTCs defined and reviewed | 0.066667 | Yes | DX-726 https://drive.google.com/drive/u/0/folders/0B4pIWUeMWeWIZG1jM2IzblNOaUE |  | 1
6 | CQM process for code version control - SVN followed | 0.066667 | NA |  |  |  | Not setup for Layer 7 policies
7 | Code quality analysis using Sonar done and changes implemented | 0.066667 | NA
8 | Unit Testing completed | 0.066667 | Yes | DX-726 |  | 1
9 | Unit test results reviewed | 0.066667 | Yes | DX-726 |  | 1
10 | Automated Build followed including automated Unit testing | 0.066667 | NA |  |  |  | Not setup for Layer 7 policies
11 | Regression pack updated | 0.066667 | No |  |  |  | Regression pack to be updated
12 | Automated Deployment followed including automated testing followed in non-prod environments | 0.066667 | NA
13 | Release pack created | 0.066667 | NA
14 | Developer Manual updated | 0.066667 | Yes |  |  |  | <SK> ref/link
15 | Project plan and RAID updated | 0.066667 | Yes | Refer Row - 26 |  |  | <SK> ???
| Build Checklist [DxG2] |  |  |  |  | 6
TESTING
1 | Environment configuration change implemented and validated | 0.055556 | No |  |  |  | There is no env change
2 | QA functional TCs reviewed | 0.055556 | Yes | DX-847 |  |  | <SK> where are the review commenst stored?
3 | CIP scripts for UAT updated | 0.055556 | Yes |  |  |  | <SK> evidence
4 | Deployment in UAT environment | 0.055556 | Yes |  |  | 1 | No Build reference : SVN is not used for the deployment, so no reference number
5 | Test data readiness for UAT/Stage testing | 0.055556 | Yes | DX-847 |  | 1 | While doing partner usage testing prepared test data
6 | Test execution in UAT/Stage environment | 0.055556 | Yes | https://drive.google.com/drive/u/0/folders/0B4pIWUeMWeWIZG1jM2IzblNOaUE |  | 1 | evidence : QA test results
7 | Defect list available with status updated | 0.055556 | Yes | https://drive.google.com/drive/folders/0B4pIWUeMWeWIZG1jM2IzblNOaUEDX-847 |  | 1
8 | Environment setup and Test data readiness for PERF testing | 0.055556 | Yes |  |  | 1
9 | Sandbox environment setup with APP test builds | 0.055556 | NA
10 | CIP scripts for PERF updated | 0.055556 | NA |  |  |  | Changes are made on JMS version
11 | Load Test and NFR test execution in PERF environment | 0.055556 | NA |  |  |  | Changes are made on JMS version
12 | 3rd party systems integration (incl APPs) , Internal Ladbrokes system and External ladbrokes system tested | 0.055556 | NA
13 | NFRs achieved | 0.055556 | NA |  |  |  | Changes are made on JMS version
14 | Operational requirements tested and met | 0.055556 | Yes | DX-847 |  | 1
15 | App testing and 3rd party system integration testing | 0.055556 | Yes |  |  |  | <SK>evidence/report/link?
16 | QA test sign-off with Test completion report | 0.055556 | Yes | QA Exit report |  |  | <QA test exit report> Will share it tomorrow
17 | Security test sign-off report | 0.055556 | NO
18 | Project plan and RAID updated | 0.055556 | Yes | Refer Row - 26 |  |  | <SK>???
| Testing Checklist [DxG3] |  |  |  |  | 6
RELEASE Readiness
1 | Version reference on Jira created/updated | 0.125 | Yes | DX-20 |  |  | <SK> why DX?
2 | Release plan updated | 0.125 | Yes | https://tools.ladbrokes.com/confluence/display/DX/EIS+Service+Categorisation |  |  | <SK> Why service categoristaion sheet?
3 | Programe RAID updated | 0.125 | Yes | https://tools.ladbrokes.com/confluence/display/DX/Release+Notes+-+DX-20 |  | 1 | <SK> HAs the RAID sheet been updated with same risks/issues etc?
4 | Release notes | 0.125 | Yes | https://tools.ladbrokes.com/confluence/display/DX/Release+Notes+-+DX-20 |  | 1
5 | Runbook (implementation, backout plan) | 0.125 | Yes | https://tools.ladbrokes.com/confluence/display/DX/Release+Notes+-+DX-20 |  | 1
6 | CAB CR submitted, reviewed and approved | 0.125 | Yes | https://docs.google.com/spreadsheets/d/1voaUyFf-2hRiJ61iZc6DvVw0acfLOGVj7kl2ag3jiDc/edit#gid=0 |  | 0 | <SK> Have ll docs been uploaded on CR?
7 | Other affected streams, 3rd Party informed about release | 0.125 | Yes | CHG0040291 |  | 0 | <SK> CR ref for what?
8 | KT and knowledge transition to L2/L3 support team | 0.125 | Yes | API Partners |  | 0 | <SK>???
| Release readiness GO/NO-GO [DxG4] |  |  |  |  | 3
RELEASE deployment & validation
1 | Deployment in PRODUCTION | 0.14286 |  |  |  | 1
2 | Deployment in PrePROD | 0.14286 |  |  |  | 0
3 | Post release Testing completed | 0.14286 |  |  |  | 1
4 | Post release Issue tracker updated | 0.14286 |  |  |  | 1
5 | Release activities completed | 0.14286 |  |  |  | 0
6 | Production Issues tracker updated | 0.14286 |  |  |  | 0
7 | Release retrospective and lessons learnt updated | 0.14286 |  |  |  | 1
| Project Closure |  |  |  |  | 4

## Deployment Checklist
Operational instructions: There should be one checklist for each service or policy This will be based on user stories planned in a sprint or project phasewise requirements defined in project plan The checklist should be prepared/updated by the DxM or PM and shared as a google drive sheet The Gates DxG0 to DxG3 should be Reviwed and Approved 1 week ahead of the Planned Release date The Gates DxG4 should be Reviewed and Approved atleast 2 working days in advance to the Planned Release date The Go/NoGo to be planned with All Key stakeholders prior to the Release in discussion with the SQM
| Description | Applicable YES/NO | Artefact location link or url | Gate Review Date <DDMMYY> | Gate Status [1-Approved, 0-Rejected] | Remark | Sign-off
| Deployment checklist | <to be added by DM and agreed with Delivery Lead | <to be added / DM> |  | <to be added by DM and agreed with Delivery Lead
1 | Approved CR details should be recived
2 | Verify the approval details in CR and check deployment window time
3 | Verify the environment details
4 | Verify svn check in is done properly with valid comments
5 | Verify code coverage is competed and include the percentage accomplished
6 | Verify percentage of unit test cases covered and report
7 | Verify the code review report and should available in shared location
8 | Verify the Munit test cases percentage of cover and report
9 | Verify the source code is mavnized and proper pom.xml is availabel in SVN
10 | Verify the proper branching structure maintained or not
11 | Verify the naming conventions for branching stratergy document
12 | All the design documents respect to the project reviewed and signed off should be available
13 | Release notes for the deployment should be shared which covers instructions for the deployment specific to the project
14 | QA test sign-off with Test completion report should avilable
15 | After deployment check the log of the server for errors and warnings
16 | Create the tag for the production release source code and verfiy whether the correct code is tagged