## Integration Projects
Program | Work Order/Change Order | Start | End | DM | $ Amount | Signature Status |  | PO# pcode | Replicon code/CG proj code | KO Lead | Current Phase | No. of integrations/API Proxy | Complexity | RYG | Comments in case R/Y or if waiting on another group
[6 empty] | KO | CG
EG SEP | WO-20160330-C-GIT-ICOE-EG-SEP-UpdateConsumer(Plural Entry) | 2016-03-28 | 2016-09-02 | VA | 7564 | Signed | Signed | No PO# | 100338613 | Pravin | On-Hold | 1 | M | G | On hold, being planned for Q4 End November. Michal yet to come back with the dates.
EG SEP | WO-20150914-C-GIT-ICOE-Apigee-EG-SEP Get Engagements API | 2015-09-14 | 2016-09-22 | VA | 8053 | Signed | Signed | 7000785813 | 100293434 | Pravin | Warranty | 1 | L | G | Deployed to production on 9/22
EG SEP | WO-20151005-C-GIT-ICOE-EG-SEP-Engagements Get Consumer | 2015-10-05 | 2016-09-22 | VA | 12139 | Signed | Signed | 7000733673 | 100284163 | Pravin | Warranty | 1 | M | G | Deployed to production on 9/22
EG SEP | WO-20150914-C-GIT-ICOE-Apigee-EG-SEP Create Engagements | 2015-11-03 | 2016-09-22 | VA | 14695 | Signed | Signed | 7000785814 | 100293433 | Pravin | Warranty | 1 | M | G | Deployed to production on 9/22
EG SEP | WO-20151005-C-GIT-ICOE-EG-SEP-Engagements Responses and Error Handling | 2015-10-05 | 2016-09-22 | VA | 26917 | Signed | Signed | 7000733671 | 100285571 | Pravin | Warranty | - | M | G | Deployed to production on 9/22
EG SEP | WO-20160201-ICOE-EG-SEP-APIGEE Find Consumer | 2016-02-01 | 2016-09-02 | VA | 8602 | Signed | Signed | No PO# | 100323071 | Pravin | On-Hold | 1 | M | G | On hold, being planned for Q4 End November. Michal yet to come back with the dates.
EG SEP | WO-20151130-C-GIT-ICOE-EG-SEP Update Consumer | 2015-11-30 | 2016-09-02 | VA | 13288 | Signed | Signed | 7000785827 | 100300006 | Pravin | On-Hold | 1 | M | G | On hold, being planned for Q4 End November. Michal yet to come back with the dates.
Freestyle | WO-20151115-C-GIT-ICOE NMS2.0 | 2015-11-26 | 2016-10-06 | KN | 52384 | Signed | Signed | 7000885018 | 190306524 | Julian | Warranty | 1 | H | G | Splunk enabled for ALL integrations in production. Integrations are still monitored by Splunk and Dev teams. One warranty defect raised yesterday. INC4512925: Failing Integration between FET and AW. This is not due to mulesoft code. AirWatch is not able to handle bulk load. AW team is working on this.
Freestyle | WO-20150924-C-GIT-ICOE_FET CMS Integration | 2015-11-11 | 2016-10-06 | KN | 25963 | Signed | Signed | 7000870248 | 190306527 | Julian | Warranty | 1 | H | G
Freestyle | WO-20151221-C-GIT-ICOE FET to NMS Relinking | 2015-11-23 | 2016-10-06 | KN | 9818 | Signed | Signed | 7000886735 | 190320136 | Julian | Warranty | 2 | H | G
Freestyle | WO-20151214-GIT-C-ICOE MDM Last Seen | 2015-11-11 | 2016-10-06 | KN | 3638 | Signed | Signed | 7000886741 | 190306540 | Julian | Warranty | 1 | L | G
Freestyle | WO-20160125-C-GIT-ICOE FDA | 2016-02-01 | 2016-10-06 | KN | 15340 | Signed | Signed | 7000887955 | 100350627 | Julian | Warranty | 1 | M | G
Freestyle | Airwatch Dragen fruit release (or NMS TRO) | 2016-10-03 | 2017-03-31 | KN | $ | Signed | Not signed | P-65380 | 100339748 | Julian | In Progress | - | M | G | Currently in Build phase. Remediating 3 integrations, enhancements for one integration and building one new integration.
Technical | ICOE EG-SEP PICASSO-GENESIS Mulesoft Integration | 2016-01-20 | 2017-01-15 | SM | 17123 | Signed | Signed | 7000850265 | 190316489 | Julian | Warranty | 1 | L | G | * Code was deployed in PROD on 10/18. * Validation with Picasso and Genesis teams still pending. Need to fast track this so that we can complete and invoice.
Marketing | WO-20160307-C-GIT-ICOE-Global Product Information API Change | 2016-03-07 | 2016-12-15 | VA | 4836 | Signed | Signed | No PO# | 100340077 | Venkat | Build | 1 | L | G | * Connectivity has been established from Cloudhub to GPDS DB * Waiting on Splunk review to migrate to TEST
Technical | WO-20160119-ICOE-C-Sample Manager Integrations Project | 2016-01-19 | 2016-11-20 | AD | 63449 | Signed | Signed | 7000855559 | 190319847 | Julian | Warranty | 3 | H | G | 2 warranty issues raised. Both resolved.
User Experience | WO-20160509-C-GIT-ICOE-Chatter Anywhere Upgrade | 2016-05-09 | 2016-10-15 | VA | 9922 | Signed | Signed | 7000872494 | 100344861 | Venkat | Warranty | 1 | L | G | Warranty in progress. Nothing to report.
Ethics & Compliance | WO-20160701-C-GIT-ICOE-Smart Simple Integration-SR-RR-1512 | 2016-07-04 | 2016-09-20 | VA | 20262 | Signed | Signed | 7000897392 | 100350666 | Kunal | Warranty | 1 | H | G | Go-live is completed on 20th Sep.Post go-live we fixed SAP data related fix changes and changes migrated to production on 14th Oct. Splunk validation pending. Sent a few reminders to that team. Need help to fastrack this.
HR | WO-20160630-C-GIT-ICOE LCOA Mulesoft Integration | 2016-08-08 | 2017-01-14 | SM | 106305 | Signed | Signed | Issued? | 100354132 | Kunal | SIT/UAT | 5 | H | G | UAT started on 10/24. Zero defects raised so far. Couple of enhancements raised during UAT. This will be managed within the CO for the extension to 11/18. Estimate for CO pending with Pravin. Need help to fastrack the approval of this.
HR | Fix the Foundations (Onboarding Nirvana) | 2016-08-01 | 2017-01-05 | SM | 31122.71 | Signed | Signed | 7000904891 | 100354132 | Wally | SIT/UAT | 1 | H | G | SIT & Regression complete and approved. CR for go-live raised for 11/5.
HR | Contingent Worker Governance | 2016-08-08 | 2017-01-12 | SM | 9359.5 | Signed | Signed | 7000905647 | 100354133 | Wally | SIT/UAT | 1 | H | G | SIT & UAT completion status pending with project team. Need help to fastrack this. Go-live date again pushed to 12/3. Pending confirmation on this to raise CO.
Marketing | WO-20160704-C-GIT-ICOE Macroeconomics Integration | 2016-06-27 | 2016-12-16 | KN | 19050 | Signed | Signed | 7000887863 | 190350669 | Kunal | UAT | 1 | M | G | Integration work complete. Go-live date pending on client. Project team has raised yet another enhancement during this time. Will add this to the pending CO.
Reusable Services | ISSCOM - CokeWorks integration | 2016-06-15 | 2016-10-24 | - | 91800 |  |  | Not Cap Proj |  | Betty | SIT | 6 | M | G | * SIT & UAT is complete. Go-live is schedled for 10/24.
Simplification | Tibco-> Mulesoft Migration -(October release - 10 integrations) | 2016-07-15 | 2016-11-18 | - |  |  |  | Not Cap Proj |  | Betty | SIT | 10 | L | R | * FUT completed for 9 integrations; 1 in-progress (encryption issue with Amex) * SIT complete for 2 out of 10 integrations. * Release exception needed for go-live on 10/02.
SAP-to-Cloud | WO-20160808-C-GIT-ICOE-SAPP08-UnixScript Migration to AxwayCFT | 2016-08-08 | 2017-04-30 | VJ |  | Signed | Signed | 7000912013 | 100354792 | Betty | Build | 24 | L | G | Project to be closed and replaced with the new TRO
Platform | TRO-20160712-C-GIT-ICOE Mulesoft LCM | 2016-08-01 | 2016-12-23 | NK | 178290 | Signed | Signed | P-00065531 | 100356537 | Venkat | In Progress | 29 | M | G | Concur Employee Data - 2 Defects Testing Completed Cost Objects - Testing in-progress. Splunk Validation in-progress - Concur, GPDS interfaces GPDS - TEST migration planned for next week. NCR - cci-to-sap Integration - Remediation changes completed, review in-progress CIC Integration - 2 Defects Fixed, Data synchronization b/w MSBI & SFDC are resolved/fixed, testing is still in-progress PBO - Code changes in-progress Freestyle – 18(Migrated on 9/19); Others - 11(Concur, ELM, ITAM, GPDS, NCR, PBO, CIC)
Finance | WO-20160804-C-GIT-ICOE-Blackline JV Integration | 2016-07-26 | 2016-10-23 | VA | 8936 | Signed | Signed | 7000904873 | 100354134 | Wally | Go-live | 1 | M | G | * Apigee code has been deployed to PROD * End-to-end testing will happen next week. Exact date pending.
Procurement | WO-20160905-C-GIT-ICOE-IT-SES File integration | 2016-08-29 | 2016-11-15 | RR | 18150 | Signed | Signed | No PO# | 100358395 | Pravin | UAT | 1 | M | G | UAT completed. Technical go-live planned for 10/28.
Reusable Services | ISSCOM - Google Data Lake integration | 2016-08-24 | 2016-11-15 | - | 75000 |  |  | Not Cap Proj |  | Kunal | Build | 1 | M | G | * Build and Unit test is in progress. * SIT is scheduled for 10/24.
Other | TRO-ICOE-TIBCO-OTM Enhancements for handling Brazil Taxes | 2016-09-26 | 2016-10-21 | AM | 1560 | Signed | Signed | P-00064970 |  |  | Build | 1 | M | G | In-progress
Other | ICOE-Apigee Virtustream Ticket Integration | 2016-09-12 | 2016-11-05 | VA | 11880 | Signed | Signed | No PO# | 100358405 | Pravin | Build | 2 | M | G | UAT in progress and will complete by 10/31. On track so far.
Concur | WO-20160928-C-GIT-ICOE Concur Global Template Mulesoft Integration | 2016-09-28 | 2017-04-04 | VJ | 85954 | Signed | Signed | 7000931523 | 100360051 | Kunal | Build | 3 | H | G | * FUT is in progress for Cost Object integration. * Employee integration will be in FUT by 10/24. * JV Feed integration is in build. Due on 11/7. On track so far. CO pending for p-card enhancement. Need help to fastrack this.
Other | ICOE-Freestyle CDO Report/Interface Axway | 2016-09-28 | 2016-10-31 | VA | 3553 | Signed | Signed | No PO# | 100358394 | Kunal | Build | 1 | L | G | We have completed the test in DEV and Test environment successfully. Waiting for Freestyle team about Go-live dates.
Other | WO-20160914-C-GIT-ICOE-Bill trust Axway Integration | 2016-09-14 | 2016-10-26 | VA | 10032 | Signed | Signed | 7000925017 | 100358396 | Kunal | RA & Design | 1 | M | G | In Dev environment, Bill Trust got confirmation from SAP and Mainframe for an end to end testing and waiting for Oracle to confirm. In TEST env, configuration still going on from AXWAY side.
Other | TRO Apigee logging solution - fix needed to remove customization | 2016-10-01 | 2016-11-30 | VA | 4330 | Signed | Signed | Issued | 100318226 | Venkat | Design | 0 | M | G | Sys logger instance on Coke environment is pending. Coordinating with the Snap team to set this up.
MARS | WO-20161017-C-GIT-ICOE MARS Enhancement | 2016-10-17 | 2017-05-15 | RR | 35123 | Not Signed | Not signed | No PO# |  | Jag | RA & Design | 3 | M | Y | WOP pending KO approval eventhough RA & Design is in progress. Requirements also not finalized.
Other | WO-20161017-C-GIT-ICOE-Apigee KOCP-BOX_Integration | 2016-10-17 | 2016-11-18 | VA | 8956 | Not Signed | Not signed | No PO# |  | Julian | RA & Design | 1 | M | G | Design in progress. No issues so far.
Other | WO-20161017-GIT-C-ICOE- Org Chart Integration | 2016-10-17 | 2017-03-09 | SM | 20776 | Signed | Signed | No PO# |  | Wally | RA & Design | 1 | M | Y | We are still waiting for mapping document and couple of other details from project team and could not complete design activity in time. Raised this concern with KO. Need help to fastrack this.
SAP-to-Cloud | TRO UNIX to Linux Remediation | [12 empty] | Y | Pravin to plug in the details post discussion with Krishnan
SAP-to-Cloud | TRO Salesforce Migration | [12 empty] | G | Pravin to plug in the details post discussion with Krishnan
| ICOE-ELM |  |  | VA
ICOE-ITAM
Note on Q19: Warranty Issues: 1. SAP R3 Design Issue -Approved Design modified due to SAP side limitation. Root cause Analysis: Not included SAP team for any SAP endpoint related integration and Signoff was not taken from SAP team. 2. MASTER DATA SYNC Issue(INC4311886) -Not given correct properties file Root cause Analysis: Incorrect Property file was uploaded against the incident (seems to be a communication gap between AM & business), as lessons learnt, Need to include AM team wherever changes to property files. 3. SAP R3 Connection Issue - In PROD environment SAP R3 wrongly configured. That was the causes of mule code not able to connect to SAP Root cause: This is due to configuration of Program Id to incorrect host in SAP Side, We have shared the design document to SAP team and have got the confirmation, but for some reasons this is slipped by SAP team but was latter corrected to fix the issue. ( This is also due to the fact that the program id for SAP R3 Prod. was ready after the Go-live and the issue for SAP endpoint for Prod has been taken as incident) 4. SM9 and SM11 Mastero Job Issue - Since SM9 and SM11 using same connection table (T_LAB_CONN_PARAM) causing Issue. Root cause: As SM9 & SM11 are using the same table, it was causing issues and only 1 job would work either SM9 or SM11 (this was communicated to Business), to resolve this we have created new key for SM11 5. SR Transformation Issue - For the field Date Manufactured mule code transform only date, not time as trigger truncate time part. Root Cause: This is not the Mule code issues, as we had issues in the sample request application, to accommodate the fix on the application, we have made changes in the mule code 6. SR MAXID Issue : Mule code uses Max_id for generating primary key for inserting T_RQST_VAL_MAP and T_SMPL_VAL_MAP table causes issue in SR application Root Cause: This is not the Mule code issues, as we had issues in the sample request application, to accommodate the fix on the application, we have made changes from Max_id to next sequence value for the primary key.

## Completed
Program | Work Order/Change Order | Start | End | DM | $ Amount | Signature Status |  | PO# pcode | Replicon code/CG proj code | KO Lead | Current Phase | No. of integrations/API Proxy | Complexity | RYG | Comments in case R/Y or if waiting on another group
[6 empty] | KO | CG
Simplification | TRO-20160602-C-GIT-ICOE MQ Assessment & Remediation | 2016-06-13 | 2016-12-31 | - | 53432 | Signed | Signed | P-00065532 | 100350039 | Venkat, Betty | In Progress | 63 | H | G
Other | TRO-ICOE-TIBCO-UAT Support-Treasury Reval Settlements Interfaces | 2016-09-15 | 2016-10-23 | - | 416 | Signed | Signed | No p-code |  |  | On-Hold | 2 | L |  |  | Add Bharat 50 Hrs for 3 weeks
Other | TRO-20160919-C-GIT-ICOE MARS Mulesoft support | 2016-09-13 | 2016-09-30 | - | 6790 |  |  | No p-code |  | Pravin | In Progress |  |  | G
Other | TRO-20160923-C-GIT-ICOE SAP Cloud Migration support | 2016-09-19 | 2016-12-30 | SK | 119250 | Signed | Signed | No p-code |  | Pravin | RA & Design |  | M | G | Project to be closed and replaced with the new TRO?
SAP-to-Cloud | ICOE Unix MQ_TIBCO MQ Migration | 2016-08-22 | 2016-04-30 | RR |  |  |  |  | 100357050 | Betty | Build | 67 | M | R | * Resource onboarding was delayed but has been resolved. - Contributing to Schedule delays; will not be able to meet 11/07 FUT start date but will be able to start FUT on ??/?? * Design for the interim solution is complete * Configuration per design is in progress * Need a design and plan of action for highly restricted integration (only 1 integration)
SAP-to-Cloud | ICOE Unix toLinux remediation | 2016-10-15 | 2016-04-30 | RR |  |  |  |  | Betty | Betty | Build | 64 | M | R | * Resource onboarding was delayed but has been resolved. - Contributing to Schedule delays; will not be able to meet 11/07 FUT start date but will be able to start FUT on ??/?? * Project plan and approach for remediation is being worked on. ETA - 10/27

## On-Hold
Program | Work Order/Change Order | Start | End | DM | $ Amount | Signature Status |  | PO# pcode | KO Lead | Current Phase | No. of integrations/API Proxy | Complexity | RYG | Comments in case R/Y or if waiting on another group
[6 empty] | KO | CG
Others | WO-20151111-C-GIT-ICOE SAP PI Conversion | 2015-12-26 | 2016-05-20 | VJ | 307306 | Signed | Not signed |  | Betty | Closed | 42 | H | R | Negative CO pending with KO
Others | WO-20150611-C-GIT-ICOE OTM Integrations Migration to Mulesoft ESB | 2016-02-21 | 2017-01-22 | RR | 24976 | Signed | Signed | 7000729208 | Betty | SIT | 14 | H | R | * On-Hold to get alignment on go-live date from OTM team
Others | TRO-20160720-C-GIT-ICOE - Technical - GoogleBigQuery Integration | 2016-07-11 | 2016-07-29 | KN | 24150 | Signed | Not signed |  | Kunal | Design | 5 | M | G | * Design phase complete with couple of unknowns. * Waiting on business to approve the estimates for rest of the phases. WO Submitted. Pending signature. Work Completed
HR | WO-20160801-GIT-C-ICOE-INFOR Integrations Axway CFT B2Bi Setup | TBD | TBD | SM | 4442 | Not signed | Not signed |  | Wally | On Hold | 1 | L | G | WO Submitted. Project went on hold
HR | Global Equity Redesign | TBD | TBD | [5 empty] | Wally | Discovery | ? | TBD | G | * Involved in discovery work, primarily with James Paul (SA) right now.
Concur | WO-20160527-C-GIT-ICOE Concur Global Template | 2016-06-01 | 2016-11-15 | VJ | 85000 | Not signed | Not signed |  | Kunal | On Hold | 4 | L | R | * Design for 2 out of 3 integration is complete. * Design is behind schedule for JV Feed integration (due to lack of requirements from business) * Need to align with BSM on estimates for build phase * At risk of meeting the Oct release date
HR | HR Workday Project Restart | TBD | TBD | RR | 193556 | - | - |  | Wally | Estimation | 13 | M | G
Other | SAP-PI Restart | TBD | TBD | [6 empty] | Estimation
Finance | WO-20160704-C-GIT-ICOE MFT Mulesoft Integration | 2016-07-04 | 2016-10-24 | VJ | 57206 | Not signed | Not signed |  |  | Kunal | On-Hold | 4 | M | G
Other | Apigee create/update | TBD | TBD | [7 empty] | On-Hold

## ICOE
Program | Work Order/Change Order | Start | End | DM | $ Amount | Signature Status |  | PO# pcode | KO Lead | Current Phase | No. of integrations/API Proxy | Complexity | RYG | Comments in case R/Y or if waiting on another group
[6 empty] | KO | CG
Others | SAP Cloud Migration - Linux remediations | 2016-09-19 | 2017-05-04 |  | 183931 |  |  |  | Pravin | Project confirmed |  |  |  | Project awarded, SOW inprogress
Others | New Bottlers Transformation - Axway | TBD | TBD |  | 3000 |  |  |  | Pravin | Estimation | 1 |  |  | Estimation sent to KO for approval
Others | 11 - NOA SAP - TIBCO mirgrations to Mulesoft | TBD | TBD |  | 241500 |  |  |  | Pravin | Estimation | 11 |  |  | Had discussion with onshore and working on estimation.
Others | 32 Int Tibco + 30 Tibco_MQ Migrations - Phase 1 | TBD | TBD |  | 563500 |  |  |  | Pravin | Estimation | 20 |  |  | Had discussion with onshore and working on estimation.
Others | 32 Int Tibco + 30 Tibco_MQ Migrations - Phase 2 | TBD | TBD |  | 1185650 |  |  |  | Pravin | Estimation | 42 |  |  | Had discussion with onshore and working on estimation.
Others | 2 Tibco High Volume migartion to Mulesfot | TBD | TBD |  | 64000 |  |  |  | Pravin | Estimation | 1 |  |  | Had discussion with onshore and working on estimation.
Others | 14 high volume TIBCO migrations to Mulesoft | TBD | TBD |  | $ 370,220.00 |  |  |  | Pravin | Estimation | 14 |  |  | Estimation sent to KO for approval
Others | 12 high volume TIBCO migrations to Mulesoft | TBD | TBD |  | 319180 |  |  |  | Pravin | Estimation | 12 |  |  | Estimation sent to KO for approval
Others | Unix Remediations | 2016-09-19 | 2017-02-24 |  | $ 186,780.00 |  |  |  | Pravin | Estimation | 55 |  |  | Estimation sent to KO for approval
Others | Unix & Tibco decommissiong | 2016-09-19 | 2016-12-02 |  | 41079 |  |  |  | Pravin | Estimation | 53 |  |  | Estimation sent to KO for approval
Others | Tresury Integrations- TIBCO Mirgrations to Muelsoft | 2016-09-19 | 2017-02-24 |  | 445104 |  |  |  | Pravin | Estimation | 15 | Complexity |  | Estimation sent to KO for approval
Other | Apigee create/update | TBD | TBD | [10 empty] | Pravin to get back on this
Note on P18: Warranty Issues: 1. SAP R3 Design Issue -Approved Design modified due to SAP side limitation. Root cause Analysis: Not included SAP team for any SAP endpoint related integration and Signoff was not taken from SAP team. 2. MASTER DATA SYNC Issue(INC4311886) -Not given correct properties file Root cause Analysis: Incorrect Property file was uploaded against the incident (seems to be a communication gap between AM & business), as lessons learnt, Need to include AM team wherever changes to property files. 3. SAP R3 Connection Issue - In PROD environment SAP R3 wrongly configured. That was the causes of mule code not able to connect to SAP Root cause: This is due to configuration of Program Id to incorrect host in SAP Side, We have shared the design document to SAP team and have got the confirmation, but for some reasons this is slipped by SAP team but was latter corrected to fix the issue. ( This is also due to the fact that the program id for SAP R3 Prod. was ready after the Go-live and the issue for SAP endpoint for Prod has been taken as incident) 4. SM9 and SM11 Mastero Job Issue - Since SM9 and SM11 using same connection table (T_LAB_CONN_PARAM) causing Issue. Root cause: As SM9 & SM11 are using the same table, it was causing issues and only 1 job would work either SM9 or SM11 (this was communicated to Business), to resolve this we have created new key for SM11 5. SR Transformation Issue - For the field Date Manufactured mule code transform only date, not time as trigger truncate time part. Root Cause: This is not the Mule code issues, as we had issues in the sample request application, to accommodate the fix on the application, we have made changes in the mule code 6. SR MAXID Issue : Mule code uses Max_id for generating primary key for inserting T_RQST_VAL_MAP and T_SMPL_VAL_MAP table causes issue in SR application Root Cause: This is not the Mule code issues, as we had issues in the sample request application, to accommodate the fix on the application, we have made changes from Max_id to next sequence value for the primary key.