## Sheet1
Activity | BuildTeam/POC | Rolled to initial dev team | Adopted across Projects
Setup jenkins server | Done? | different from POC server? | N/A
Setup Nexus Server | Done? | different from POC server? | N/A
Create service accounts needed | Done? | N/A | N/A
Verify deployment to CH | Done?
Verify Deployment to on prem server | Done?
Create parent Pom file for CH | Done?
Update parent pom file for on prem server | Done?
Create parameterized version of parent pom | Done? | N/A | N/A
Create sample CH project with pom using parent pom | Done? | Demo project
Create sample on prem project with pom using parent pom | Done? | Demo poject
Create sample SAP project for CH | In Progress (DLL file issue)
Create sample SAP project for on prem | In progress?
Create instructions for developers | In progress?
LCM overall design and Approach documentation | In progress?
Munit add ot parent pom | Done?
Create sample non SAP project using mUnit | Done?
Create sample SAP project using Munit | In Progress (DLL file issue)
Add parent pom to nexus
Create jenkins job for logging framework
Create jenkins job for error handling framework.
Add SOAP UI invocation to parent pom | In progress? - initally Ajay testing locally
Create guidelines for SOAP UI project level artifacts/test cases
Add SOAP UI test cases to CH sample
Add SOAP UI test case for On prem sample
Define and document code promotion process across environments
Define and document code promotion process for hot fixes
Add property handling during deployments.
Add handling of secured properties for projects
Create jenkins job to move code to QA based on a manual trigger
Validate code promotion for a sample project - Update based on feedback
Create jenkins job to move code to UAT based on manual trigger
Verify boundary conditions for automated build ( error cases )
Validate S3 in place of nexus for repo
App versioning
Availability and recovery ( improve/evaluate)
Common version/info - Inject an index page that gives info on app ( connectors used, version, build date etc…)
Common health check