## Sheet1
Capability / | Availability | Cap Status | List of Deliverables | Dependency | Target Date | Category | Applicable phase | Priority / Sequence | Current Maturity | Ajay Updates | Comments | Desired Maturity @3M | Desired Maturity @6M | desired maturity @9M | Open items / next steps
Skill - Matrix, Levels | Y |  |  |  |  | People |  | Medium /2 | 1
Project Size VS Capacity Matrix | N |  |  |  |  | People |  | High / 1 | 0
Job Descriptions | Y |  |  |  |  | People |  | Medium /2 | 2
Resource availability , Traceability | N |  |  |  |  | People |  | Medium /5 | 1
Roles & responsibility Identified | Y |  |  |  |  | People |  | High /1 | 2
Onboarding new vendor (shortlisted vendor ) | [5 empty] | Process |  |  | 2
Development process (Agile/Semi-Waterfall) | [5 empty] | Process |  |  | 2
Continuous Integration Process Code promotion process - Regular builds and Hot fixes. | N | Y | 1. currenlty working in local jenkis server, Need to implement Coke Jenkins servers with coke projects Report generations - completed locally ( once Jenkins server isssue resolved , wil complete activity by 1 week) | Access permission dependency on Coke Jenkins Server- Ajay/Venkat | Tentative Date - 10th Nov | Process |  |  | 1
Continuous Delivery/deployment process | N | Y | 1. currenlty working in local jenkis server, Need to implement Coke Jenkins servers with coke projects Report generations - completed locally ( once Jenkins server isssue resolved , wil complete activity by 1 week | Access permission dependency on Coke Jenkins Server- Ajay/Venkat | Tentative Date - 10th Nov | Process |  |  | 1
Platform Lifecycle management process Upgrade process - Mule version / hot patches upgrade , on prem- cloud, connector upgrades ,testing /certification process etc. | [5 empty] | Process |  |  | 1
Talent engine / training /Evaluation processes Developer skill evaluation process - Ability to ensure developer skill level. - Mule, Integration best practices, Ancillary tools like maven/SOAPUI etc. | [5 empty] | Process |  |  | 0
Developer /Architect on-boarding process - Run book for onboarding developer ( dev machine setups needed, access they need to request etc.). Developer Off-boarding process - Revoking access to CH, SVN etc. | [5 empty] | Process |  |  | 1
Performance testing strategy and process. | [5 empty] | Process |  |  | 1
Test driven development methodology | [5 empty] | Methodology | Enablement | High / 1 | 0
Integration implementation patterns | Y | NA |  |  |  | Patterns /Standards | Enablement | High / 1 | 2 | [5 empty] | Ashish tow work with Ajay for patterns
Integration requirements document template | Y | NA |  |  |  | Patterns /Standards | Enablement | High / 1 | 3
Integration solution design template | Y | NA |  |  |  | Patterns /Standards | Enablement | High / 1 | 3
Platform Security Patterns / Standards |  | Y | 1. Prepartion of documents which provides detailed steps for implementation security patterns in coke projects 1. PGP Encryption process 2. Secured application properties - cloudhud security processs 3. webservices security authentification processs ( if avaialble in Coke Projects) 4. Other security best practices can be implemented |  | 2016-11-10 | Patterns /Standards | Enablement | High / 1 | 2
Logging/Monitoring/Alerts Patterns / Standards - Templates |  | Y | 1. Exception Logging process - Project template which cover generic exception handling process and document which provides detail 2. Alert Pattern- Splunk logging enablement (Alerts 3. Logging standards |  | 2016-11-10 | Patterns /Standards | Enablement | High / 1 | 3
Unit/SIT/UAT test standards |  | Y | 1. Unit Testing Standards |  | 2016-11-10 | Patterns /Standards | Enablement | High / 1 | 1
Regression test standards |  | Y | 2. Regression testing standards- How to handle regression testing and standar |  | 2016-11-15 | Patterns /Standards | Enablement | High / 1 | 2
Project plan template ( right dependency, sequencing of items such as firewall rules etc., DNS/other infrastructure activities) mainly for LCM, Deployment & SDLC | [5 empty] | Patterns /Standards | Enablement |  | 1
Enabling Platform Monitoring / Notification, alerts capabilities to Ko Standards | [5 empty] | Monitoring / Notification | Enablement |  | 2
Monitoring/Notification/alerts based on platform performance - decay , bottlenecks / idle | [5 empty] | Monitoring / Notification | Enablement |  | ?? | 1
Monitoring/Notification/alerts potential unauthorized attacks / access attempts | [5 empty] | Monitoring / Notification | Enablement |  | ?? | 0
Graceful recovery and exception handling | [5 empty] | Patterns / Standards |  |  | 1
Governance Model - Logical - Decision making/ Planning / escalation / Business Content / Communication | [5 empty] | Governance |  |  | 1
Governance Model - Physical | [5 empty] | Governance |  |  | 1
Operating Model to ensure governance across all processes | [5 empty] | Governance |  |  | 0
Development Tools / Version / Code Compliance checklist / verification for developers / testers | [5 empty] | Governance |  | Venkat to send input | 2
Business Requirement complete checklist / scorecard
Code review checklist | Y |  |  |  |  | Governance |  | Venkat to send input | 1
Design review checklist | Y |  |  |  |  | Governance |  | Venkat to send input | 1
Automated -Code review | [5 empty] | Governance |  |  | 1 | 0 | Approach yet to be finalized so I would call this 0
test Case review . Result review check list (Capability to verify test cases run Automated/Semi-Automated) | [5 empty] | Governance |  |  | 2
Automated regression testing - At platform upgrades/every CD cycle | [5 empty] | Governance |  |  | 2 | 1 | I havent seen these so not sure if they are there but if they are there it can be a 2
Automated notification/alerts to project team for failures, in-compatibility issues | [5 empty] | Governance |  |  | 1
Automated deployment decision making based on code coverage / test results |  | Done | Completed on local jenkins Coke Server tentative target date - 10-Nov | Access permission dependency on Coke Jenkins Server- Ajay/Venkat | Completed on local jenkins Coke Server tentative target date - 10-Nov | Governance |  |  | 2 | 1 | Can be done as part of LCM nut currently absent
Define of platform Access control | [5 empty] | Governance |  |  | 2
Security audits - Compliance / Support Security testing/audit - NPI data, and services security levels are being met. | [5 empty] | Governance |  |  | 3 | 2 | Best practices are probably documented but audit and review need to be done. If they are being done currently we can make this a 3.
Deployment checklist | Y |  |  |  |  | Governance |  |  | 1
Pricing/Usage/Capacity realization / auditing Usage reporting - worker and performance metrics reporting for optimization and proactive alerting. | [5 empty] | Governance |  |  | 3?? | 2 | APIS are available to read these + splunk should feed some of this. However don’t think this is there currently.
Software Configuration Management document | Y | [7 empty] | 1 | 2 | I believe there is a document. Not a great one but more a copy from a differnet project AFAIK but we have a base so I would call this a 2.
Non functional testing/Audit process - load balancing, DR adherence verification | [5 empty] | Governance |  |  |  | 2 | Process is defined to some level though not close to ideal state.
Interface intake/Details maintenance process- Integration categorization/tagging, identify concerned systems, versions being used ( mule, connectors) | [5 empty] | Service Repository/Discovery/Reusability |  |  |  | 1 | Missing completely. Reason for alling this 1 is there are some ways to call mule apis and extract these to some level.
Interface inventory - discoverability of interfaces for reuse and consumption. | [5 empty] | Service Repository/Discovery/Reusability |  |  |  | 1 | Missing completely. Reason for alling this 1 is there are some ways to call mule apis and extract these to some level.
Interface / integration Service Discovery , search, promotion , demotion, release version mgmt. through repository | [5 empty] | Service Repository/Discovery/Reusability |  |  |  | 1 | Missing completely. Reason for alling this 1 is there are some ways to call mule apis and extract these to some level.
Code sample for Integration implementation Patterns | [5 empty] | Samples / Reusable Components |  | Venkata | 2
Code samples / Components for Authentication / Security/encryption | [5 empty] | Samples / Reusable Components |  | Venkata | 2
Exception/Error handling reusable components | [5 empty] | Samples / Reusable Components |  | Venkata | 1
Common Pub-Sub Pattern components | [5 empty] | Samples / Reusable Components |  | Venkata | 3
reusable components for common flows like s3,SNS, Web service, DB , SAP Adapter | [5 empty] | Samples / Reusable Components |  | Venkata | 3
Cloud Hub to On-Prem connectivity / reusable flow | [5 empty] | Samples / Reusable Components |  | Venkata | 3

## Maturity
0 - Conceptual / None
1 - Initial - Ad-Hoc
2 - Repeatable / Opportunistic
3. Defined & Systematic
4. Measured / Automated
5. Optimized ( Auto-run)